## 🔄 OSS Changes
✅ Open-Source Tool Replacements Summary
All paid/proprietary services replaced with free, self-hostable open-source alternatives
Layer | Original (Paid) | Replacement (OSS) | Why Better | Self-Hosted? | Cost
Notifications | Firebase Cloud Messaging (Google) | Ntfy.sh (self-hosted) | No Google dependency; simple HTTP API; push to iOS, Android, Web; fully self-hosted | ✅ Yes | Free
Notifications (alt) | OneSignal / AWS SNS | Gotify (self-hosted) | Lightweight, simple REST API, Android & desktop push, Docker-ready | ✅ Yes | Free
SMS OTP | Twilio / MSG91 (paid per SMS) | Plivo (free trial) + Termii | Plivo has India support & lower rates; Termii has free sandbox tier; same SMS API pattern | ❌ SaaS | Low cost / Free tier
Error Tracking | Sentry (5k events free, then paid) | GlitchTip (self-hosted) | 100% Sentry-compatible DSN; unlimited events self-hosted; uses same Sentry SDK | ✅ Yes | Free
Logging & Monitoring | Datadog / Logtail (paid) | Grafana + Loki + Promtail | Industry standard OSS stack; powerful dashboards; scales with Prometheus | ✅ Yes | Free
CDN & Security | Cloudflare Pro (paid) | Cloudflare Free + Nginx + Fail2ban | Free Cloudflare plan covers DDoS + CDN; Fail2ban protects origin server | ✅ Partial | Free
PaaS / Hosting | Vercel (paid for teams) | Coolify (self-hosted PaaS) | One-click app deployments like Heroku/Vercel but fully self-hosted; supports Next.js | ✅ Yes | Free
Flutter Push Config | Firebase (google-services.json) | Ntfy.sh HTTP API in app | No Firebase dependency; call ntfy HTTP endpoint directly from Flutter app | ✅ Yes | Free
App Distribution (Android) | Google Play ($25 one-time) | F-Droid + APK direct install | For internal church community; distribute APK via QR code or F-Droid repo — no store needed | ✅ Yes | Free
App Distribution (iOS) | Apple Developer ($99/yr) | PWA (Progressive Web App) | For iOS, publish as PWA; members install via Safari 'Add to Home Screen' — no Apple fee | N/A | Free

## 📱 App Modules
⛪ Church Community App — Module Overview
Comprehensive feature breakdown with priority, complexity & user roles
Module | Core Features | Admin Controls | Target Users | Priority | Complexity | Status
🏠 Home | Birthdays, feast announcements, daily Bible verse, prayer schedule, upcoming events banner | Edit banners, schedule Bible quotes, push notifications, set prayer times, manage announcements | All Members | 🔴 Critical | Medium | 🟡 In Design
👥 Members | Directory with photos, search & filter, role badges, alumni section, teams with their leaders and members, member profiles, share the image option | Add/edit/delete members, bulk import (CSV/Excel), assign roles & teams, archive members, export list | All Members / Admin | 🔴 Critical | High | 🟡 In Design
📅 Calendar | Church events, birthdays, meetings, feast days, prayer sessions, recurring events support | Create/edit/delete events, set reminders, publish to members, manage recurring schedules | All Members | 🔴 Critical | Medium | 🟡 In Design
🖼️ Media | Photo albums, event-linked albums, search by date/event, share & download | Upload/manage/delete media, create albums, tag events, control visibility (public/team) | All Members / Media Admin | 🟠 High | Medium | ⚪ Planned
🔔 Notifications | Birthday alerts, event reminders, emergency announcements, feast day alerts, prayer time reminders | Send to all / specific teams / individual members, schedule notifications, view delivery logs | Admin / Team Leaders | 🔴 Critical | Low | 🟡 In Design
🙏 Prayer Schedule | Daily/weekly prayer slots, member-wise duty assignment, prayer group rotation | Assign prayer duties, edit schedule, send reminders to assigned members | All Members / Secretary | 🟠 High | Medium | ⚪ Planned
📣 Announcements | Pinned announcements, urgent alerts, feast/holiday messages, expiry date for posts | Create/pin/delete announcements, set expiry, target audience selection | President / Super Admin | 🟠 High | Low | ⚪ Planned
👨‍👩‍👧 Teams | Team directory, member roster per team, team events, team leader contact | Create/edit/delete teams, assign members & leaders, link events to teams | Team Leaders / Admin | 🟡 Medium | Medium | ⚪ Planned
📖 Bible & Devotion | Daily verse (auto), weekly devotion articles, bookmarking, sharing verse to WhatsApp/social | Schedule verses, add custom devotion content, manage article library | All Members | 🟡 Medium | Low | ⚪ Planned
ℹ️ About Us | Organization history, vision & mission statement, current executive committee with photos & roles, past presidents list, founding story, official contact info, social media links | Edit about text (rich text), upload/replace committee photos, update office bearer details, manage social links | All Members / Public | 🟠 High | Low | ⚪ Planned

## 🛠️ Tech Stack
⚙️ Technology Stack & Architecture
Tools, justification, version notes & alternatives for each component
Layer | Component | Tool / Tech | Purpose | Why Chosen | Alternatives | Notes
Frontend | 📱 Mobile App | Flutter 3.x | iOS & Android app | Single codebase saves 40% dev time; near-native performance; strong community | React Native, Kotlin/Swift | Use Flutter Flavors for dev/prod environments
Frontend | 🖥️ Admin Panel | Next.js 14 (App Router) | Web dashboard & CMS | SSR for fast load; file-based routing; easy API integration; Coolify (self-hosted) deployment | Nuxt.js, SvelteKit, Remix | Host on Coolify (self-hosted) or self-host with Docker
Backend | 🔌 API Server | NestJS (Node.js) | RESTful / GraphQL API | Modular architecture, TypeScript, built-in validation, scalable for teams | Express, Fastify, Django | Use class-validator for DTO validation
Database | 🗄️ Primary DB | PostgreSQL 15+ | Members, events, roles | ACID compliance; relational data fits church model; rich query support | MySQL, SQLite, MongoDB | Use Prisma ORM for type-safe queries
Storage | 🗂️ File Storage | MinIO (S3-compatible) | Photos, videos, documents | Open-source, self-hosted, no vendor lock-in, S3 API compatible | AWS S3, Cloudflare R2 | Set lifecycle rules to compress old media
Notifications | 🔔 Push Alerts | Ntfy.sh (self-hosted) | Real-time push notifications | Free tier sufficient; supports iOS + Android; reliable delivery | Gotify, Gotify | Store FCM tokens per device in DB
Auth | 🔐 Authentication | JWT + OTP (SMS/Email) | Secure login, role access | Stateless JWT scales well; OTP adds security without passwords | Supabase Auth, Auth0, Clerk | Use refresh tokens; OTP via Plivo (free tier) / Termii
Automation | ⏰ Scheduler | NestJS Cron (node-cron) | Automated timed tasks | Built into NestJS; no extra infra needed for basic scheduling | BullMQ, Celery, Agenda.js | Move to BullMQ if queue grows complex
Infra | 🌐 Reverse Proxy | Caddy 2 | SSL termination + routing | Auto-HTTPS via Let's Encrypt; minimal config vs Nginx | Nginx, Traefik, HAProxy | Use Caddyfile for simple multi-app routing
Infra | 🛡️ CDN & Security | Cloudflare Free / Nginx + Fail2ban | DDoS protection + caching | Free plan covers most needs; global CDN; analytics included | Cloudflare Free / BunnyCDN, Cloudflare Free | Enable Bot Fight Mode and WAF rules
DevOps | 🐳 Containerization | Docker + Docker Compose | Consistent environments | Portable across dev/staging/prod; simple multi-service orchestration | Podman, Kubernetes (later) | Use named volumes for DB persistence
DevOps | 🔄 CI/CD | GitHub Actions | Automated testing & deploy | Free for public repos; tight GitHub integration; matrix builds | GitLab CI, CircleCI | Set up staging + production pipelines
Monitoring | 📈 Logging | Winston + GlitchTip (self-hosted) | Error tracking & logs | Winston for structured logs; GlitchTip (self-hosted) captures real-time exceptions | Grafana + Loki, Grafana + Loki, Grafana | Set GlitchTip (self-hosted) alert thresholds to avoid noise

## 🔐 Admin Roles
🔐 Admin Roles & Permission Matrix
Granular access control for each role across all modules
Permission / Module | Super Admin | President | Secretary | Media Admin | Team Leader | Member | Alumni
── MEMBER MANAGEMENT ──
Add / Edit Members | ✅ | ❌ | ✅ | ❌ | ❌ | ❌ | ❌
Delete / Archive Members | ✅ | ❌ | ✅ | ❌ | ❌ | ❌ | ❌
Import Members (CSV) | ✅ | ❌ | ✅ | ❌ | ❌ | ❌ | ❌
View Member Directory | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | 👁 Limited
Assign Roles & Teams | ✅ | ❌ | ✅ | ❌ | ❌ | ❌ | ❌
── EVENTS & CALENDAR ──
Create / Edit Events | ✅ | ✅ | ✅ | ❌ | 🔶 Own Team | ❌ | ❌
Delete Events | ✅ | ✅ | ✅ | ❌ | ❌ | ❌ | ❌
View Calendar | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
── MEDIA ──
Upload Photos / Videos | ✅ | ❌ | ❌ | ✅ | 🔶 Own Team | ❌ | ❌
Delete Media | ✅ | ❌ | ❌ | ✅ | ❌ | ❌ | ❌
View Media Gallery | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
── NOTIFICATIONS ──
Send to All Members | ✅ | ✅ | ❌ | ❌ | ❌ | ❌ | ❌
Send to Teams | ✅ | ✅ | ✅ | ❌ | 🔶 Own Team | ❌ | ❌
── ANALYTICS ──
View Full Dashboard | ✅ | ✅ | ❌ | ❌ | ❌ | ❌ | ❌
Export Reports | ✅ | ✅ | ❌ | ❌ | ❌ | ❌ | ❌
── SYSTEM ──
Manage Admin Accounts | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌
App Settings / Config | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌
View Audit Logs | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | ❌

## 🗄️ Database Schema
🗄️ Database Schema — Table Definitions
PostgreSQL table structure with field types, constraints & relationships
Table | Field Name | Data Type | Constraints | Description | Relationships
Members | id | UUID (PK) | NOT NULL, AUTO | Unique member identifier | Referenced by Teams, Events, Media
Members | full_name | VARCHAR(150) | NOT NULL | Member's full name
Members | email | VARCHAR(255) | UNIQUE, NOT NULL | Login email address
Members | phone | VARCHAR(20) | UNIQUE | Phone for OTP auth
Members | role_id | UUID (FK) | NOT NULL | Assigned role | → Roles.id
Members | team_id | UUID (FK) | NULLABLE | Team membership | → Teams.id
Members | dob | DATE | NOT NULL | Date of birth (for birthday automation)
Members | photo_url | TEXT | NULLABLE | Profile photo stored in MinIO
Members | is_alumni | BOOLEAN | DEFAULT false | Alumni status flag
Members | is_active | BOOLEAN | DEFAULT true | Soft-delete flag
Members | joined_at | TIMESTAMP | DEFAULT NOW() | Registration date
Teams | id | UUID (PK) | NOT NULL, AUTO | Unique team ID
Teams | name | VARCHAR(100) | NOT NULL, UNIQUE | Team name (e.g., Youth Wing)
Teams | leader_id | UUID (FK) | NULLABLE | Team leader reference | → Members.id
Teams | description | TEXT | NULLABLE | Team purpose/description
Events | id | UUID (PK) | NOT NULL, AUTO | Unique event ID
Events | title | VARCHAR(200) | NOT NULL | Event title
Events | event_date | TIMESTAMP | NOT NULL | Date & time of event
Events | is_recurring | BOOLEAN | DEFAULT false | Recurring event flag
Events | team_id | UUID (FK) | NULLABLE | Linked team (if team event) | → Teams.id
Events | created_by | UUID (FK) | NOT NULL | Admin who created event | → Members.id
Notifications | id | UUID (PK) | NOT NULL, AUTO | Notification record ID
Notifications | title | VARCHAR(200) | NOT NULL | Notification heading
Notifications | body | TEXT | NOT NULL | Full notification text
Notifications | target_type | ENUM | NOT NULL | 'all' ¦ 'team' ¦ 'individual'
Notifications | target_id | UUID | NULLABLE | Team or Member ID if targeted
Notifications | sent_at | TIMESTAMP | DEFAULT NOW() | Send timestamp
Media | id | UUID (PK) | NOT NULL, AUTO | Media file ID
Media | file_url | TEXT | NOT NULL | MinIO storage URL
Media | media_type | ENUM | NOT NULL | 'photo' ¦ 'video' ¦ 'document'
Media | event_id | UUID (FK) | NULLABLE | Linked event album | → Events.id
Media | uploaded_by | UUID (FK) | NOT NULL | Uploader reference | → Members.id
BibleQuotes | id | UUID (PK) | NOT NULL, AUTO | Verse record ID
BibleQuotes | verse_text | TEXT | NOT NULL | Bible verse content
BibleQuotes | reference | VARCHAR(100) | NOT NULL | e.g., John 3:16 (NIV)
BibleQuotes | scheduled_date | DATE | NULLABLE | Specific display date
PrayerSchedules | id | UUID (PK) | NOT NULL, AUTO | Prayer slot ID
PrayerSchedules | member_id | UUID (FK) | NOT NULL | Assigned member | → Members.id
PrayerSchedules | slot_time | TIME | NOT NULL | Prayer time slot
PrayerSchedules | day_of_week | SMALLINT | NOT NULL | 0=Sun ... 6=Sat
Roles | id | UUID (PK) | NOT NULL, AUTO | Role record ID
Roles | role_name | VARCHAR(50) | NOT NULL, UNIQUE | e.g., Super Admin, Secretary
Roles | permissions | JSONB | NOT NULL | Permission flags as JSON object
Alumni | id | UUID (PK) | NOT NULL, AUTO | Alumni record ID | → Members.id
Alumni | member_id | UUID (FK) | NOT NULL, UNIQUE | Reference to original member
Alumni | graduation_year | SMALLINT | NOT NULL | Year left active membership

## ⏰ Automation Jobs
⏰ Automation Jobs & Cron Schedule
All scheduled background tasks with timing, trigger logic & status
Job Name | Trigger / Cron | Description | Notification Target | Conditions / Logic | Priority | Status | Est. Impact
🎂 Birthday Reminder | 0 8 * * * (Daily 8 AM) | Query members whose birthday matches today's date and send a personalized birthday notification | Individual Member + All Members (announcement) | Check dob = TODAY(); skip if is_active = false; send 2 msgs: personal + group shoutout | 🔴 Critical | 🟢 Active | High morale boost
📖 Daily Bible Verse | 0 6 * * * (Daily 6 AM) | Pick scheduled or random verse from BibleQuotes table and push to all members' home screen | All Members | If scheduled_date = TODAY() → use that verse; else pick random; mark as used | 🔴 Critical | 🟢 Active | Daily engagement
🙏 Prayer Time Alert | Based on PrayerSchedules table | Remind assigned member 15 mins before their prayer slot starts | Individual assigned member | Query PrayerSchedules where slot_time - 15min = NOW() and day_of_week = TODAY() | 🔴 Critical | 🟡 In Progress | Spiritual discipline
📅 Event Reminder — 1 Day | Daily 9 AM check | Send reminder to all members (or team) for events happening the next day | All Members / Linked Team | Query Events where event_date BETWEEN NOW() AND NOW()+24hr; send if not reminded | 🔴 Critical | 🟢 Active | Better attendance
📅 Event Reminder — 1 Hour | Hourly check | Send a final reminder 1 hour before any event starts | All Members / Linked Team | Query Events where event_date BETWEEN NOW() AND NOW()+1hr; send if not already sent | 🟠 High | 🟡 In Progress | Last-minute attendance
✝️ Feast Day Announcement | 0 7 * * * (Daily 7 AM) | Check liturgical calendar for today's feast/saint day and push an announcement | All Members | Match today's date from feast_days config table; format message with saint info | 🟠 High | ⚪ Planned | Cultural connection
🎉 Monthly Birthday Summary | 0 9 1 * * (1st of month) | Send all members a list of birthdays for the current month | All Members | Query members WHERE MONTH(dob) = CURRENT_MONTH; sort by day; format list notification | 🟡 Medium | ⚪ Planned | Community warmth
🔄 Media Cleanup | 0 2 * * 0 (Sunday 2 AM) | Delete orphaned media files in MinIO that are no longer referenced in DB | None (background task) | Compare MinIO object list vs Media table; delete unreferenced objects older than 30 days | 🟢 Low | ⚪ Planned | Storage savings

## 🗺️ Roadmap
🗺️ Project Roadmap — Phased Delivery Plan
4-phase rollout with milestones, deliverables & success metrics
Phase | Timeline | Key Deliverables | Modules Covered | Success Metrics | Dependencies | Status
Phase 1 🏗️ Foundation | Weeks 1–4 | • Project setup & repo • DB schema design • Auth system (JWT + OTP) • Admin panel skeleton • CI/CD pipeline | Auth, Members (basic), Roles | • Dev env running • Login working • 0 critical bugs | Server provisioned, Domain ready | 🟡 Planning
Phase 2 👥 Core Features | Weeks 5–10 | • Member directory CRUD • Calendar & events • Home screen (app) • Birthday automation • Daily Bible verse cron | Home, Members, Calendar, Notifications (basic) | • 50+ test members added • Birthday alert tested • App runs on both platforms | Phase 1 complete | ⚪ Upcoming
Phase 3 🖼️ Media & Notifications | Weeks 11–14 | • Photo/video upload (MinIO) • Album management • Full notification system • Prayer schedule • Team management | Media, Notifications, Prayer, Teams | • 10+ albums uploaded • Push notification delivery >95% • Prayer duty alerts working | Phase 2 complete, MinIO configured | ⚪ Upcoming
Phase 4 📊 Analytics & Polish | Weeks 15–18 | • Analytics dashboard • Attendance tracking • Report export (PDF) • UI polish & testing • App store submission | Analytics, All modules (refinement) | • Dashboard showing real data • App approved on Play Store & App Store • <2s load time | Phase 3 complete, Test users onboarded | ⚪ Upcoming

## 📐 App Screens
📐 Flutter App — Complete Screen Design Spec (iOS & Android)
Every screen: UI layout, user actions, API calls, navigation — Photos only, no video. Spreadsheet import is website-only.
Screen | Route / Name | Purpose | UI Elements & Layout | User Actions | Data Source / API | Navigation Flow | Notes
── ONBOARDING & AUTH ──
🚀 Splash Screen | / splash | App intro, checks auth token | Centered org logo on navy gradient Tagline text Version number at bottom | None — auto redirect | None (local) | → Login (no token) → Home (token valid) | Check JWT on load; 2s display
🔐 Login Screen | / login | Member login via phone OTP | Org logo (top centre) Phone number input with +91 country flag 'Send OTP' primary button 'Contact Admin' link at bottom | Enter phone number Tap Send OTP | POST /auth/send-otp | → OTP Verify Screen | Validate phone format before sending; show error inline
🔢 OTP Verify Screen | / otp-verify | Verify 6-digit OTP from SMS | 6-box OTP input (auto-advance between boxes) 60s countdown timer Resend OTP link (active after timer) Verify button | Enter OTP digits Tap Verify Tap Resend after 60s | POST /auth/verify-otp | → Home Screen | Save JWT + refresh token to Flutter secure storage
── MAIN NAVIGATION ──
🏠 Home Screen | / home | Main dashboard — daily content hub | Top bar: greeting ('Good morning, [Name]') + profile avatar (top right) Banner carousel: feast/event announcements (auto-scroll 5s) Today's Birthdays strip: circular photos + names (horizontal scroll) Daily Bible Verse card: verse text + reference + Share button Upcoming Events: next 3 events as cards Prayer Timing card: today's assigned member Bottom nav bar: Home ¦ Members ¦ Calendar ¦ Media ¦ More | Tap birthday → Member Profile Tap event card → Event Detail Tap verse Share → share image Tap banner → Announcement Detail Tap avatar → Settings | GET /home/feed GET /bible/today GET /events?upcoming=3 | Bottom nav tab 1 → Member Profile → Event Detail → Announcement | Pull-to-refresh; 15 min cache; birthday strip hidden if no birthdays today
👥 Members Screen | / members | Full alphabetical member directory | Sticky search bar at top Filter chips row: All ¦ [Team names] ¦ Alumni Sort label: 'A–Z' Member list cards: circular photo + Full Name + Team badge Alphabetical section headers (A, B, C…) No FAB import button (import is website-only) | Type in search → live filter by name Tap filter chip → filter by team Tap member card → Member Profile | GET /members?sort=name | Bottom nav tab 2 → Member Profile | Alphabetical A–Z default; lazy load 20/page; show placeholder avatar if no photo
👤 Member Profile Screen | / members/:id | Individual member detail | Full-width header with member photo (tap to fullscreen) Circular avatar overlay at bottom of header Name (large bold) + Role badge + Team chip Info section: Phone (tap to call), DOB, Join Year Team section: small photos of teammates Share Profile button → exports styled member card image | Tap photo → fullscreen photo viewer Tap phone number → dial Tap Share → share image card Admin only: Edit button (top right) | GET /members/:id | ← Members Screen → Edit Member (admin only) | Share card is a pre-rendered image with org branding; no video content anywhere
📅 Calendar Screen | / calendar | Events and birthdays calendar | Month grid view (default) Coloured dots on dates: 🔵 Event ¦ 🟡 Birthday ¦ 🔴 Feast day Selected date shows event list below grid List view toggle (top right) Admin FAB: + Add Event | Tap date → show that day's items below Tap event card → Event Detail Swipe left/right → prev/next month Admin: tap FAB → Create Event | GET /events?month=YYYY-MM GET /birthdays?month=YYYY-MM | Bottom nav tab 3 → Event Detail → Create/Edit Event (admin) | Feast days from local liturgical config file
📋 Event Detail Screen | / events/:id | Full event information | Hero banner photo (or default church banner) Event title, date + time, location Description (rich text, scrollable) Team tag chip (if team event) Share button: exports event card image Add to Calendar button (ics) | Tap Share → share event image Tap Add to Calendar → opens phone calendar Admin: Edit / Delete (top-right menu) | GET /events/:id | ← Calendar ← Notifications ← Home events list | No video; banner is photo only
🖼️ Media Screen | / media | Photo gallery — no videos | Top tabs: All Albums ¦ Events ¦ Teams Album grid (2-column cards): cover photo + album name + photo count Search bar Admin upload button (top right) | Tap album → Album Detail Admin: tap upload → pick photos from gallery | GET /media/albums | Bottom nav tab 4 → Album Detail | PHOTOS ONLY — no video support in app. Videos removed entirely from mobile.
🖼️ Album Detail Screen | / media/albums/:id | Photos inside one album | Header: album name + event tag 3-column photo grid Select mode on long press (checkboxes appear) Photo count label | Tap photo → Full Screen Viewer Long press → select mode → share/download selected Admin: delete selected | GET /media/albums/:id/photos | ← Media Screen | Full screen viewer supports pinch-zoom and swipe between photos
🔔 Notifications Screen | / notifications | Inbox of all received notifications | Notification cards: icon (type-based) + title + body preview + relative time Unread blue dot indicator Filter tabs: All ¦ Unread ¦ Birthday ¦ Events ¦ Alerts Mark All Read button | Tap notification → linked screen (event/member/announcement) Swipe right to dismiss Tap Mark All Read | GET /notifications (user-scoped) | Bottom nav tab 5 (More → Notifications) Badge count on nav icon | Badge shows unread count; clears on screen open
── MORE / SIDE MENU ──
☰ More / Side Drawer | / more | Navigation hub for secondary screens | User avatar + name + role at top Menu items list: • 🙏 Prayer Schedule • 📖 Bible & Devotion • 📣 Announcements • 👨‍👩‍👧 Teams • ℹ️ About Us ← NEW • ⚙️ Settings • 🚪 Logout | Tap any item → navigate to screen Tap Logout → confirm dialog → Login screen | None | Swipe from left edge or tap ☰ in nav bar | Accessible from bottom nav 'More' tab or swipe gesture
ℹ️ About Us Screen | / about | Organization info, history & leadership — NEW | SECTION 1 — Hero Banner Org logo + name (large) + founding year Tagline / motto SECTION 2 — About the Organization Rich text: history, vision, mission Founder photo + short bio SECTION 3 — Current Executive Committee Card grid: circular photo + name + designation (President, Vice President, Secretary, Treasurer, etc.) Tap card → member profile SECTION 4 — Past Presidents Timeline list: photo + name + year range SECTION 5 — Contact & Links Phone, email, address Social media buttons: WhatsApp ¦ Instagram ¦ Facebook Tap → opens respective app | Tap committee member photo → Member Profile Tap social link → opens external app Scroll through sections | GET /organization/about GET /organization/committee GET /organization/past-presidents | ← More / Side Drawer | All content editable from admin website. Photos displayed only — no videos. Highlight current year's committee.
🙏 Prayer Schedule Screen | / prayer | Weekly prayer duty timetable | Week view grid (7 days × time slots) Each slot: member photo thumbnail + name Today column highlighted My Duty tab: shows only current user's upcoming slots | Tap slot → member detail popup Swipe left/right → next/prev week Admin: tap slot → reassign member | GET /prayer/schedule?week=current | ← More Drawer | Push notification 15 min before assigned slot
📖 Bible & Devotion Screen | / devotion | Daily Bible verse + devotional content | Today's Verse card: large styled text + reference + version badge Share button → generates verse image for WhatsApp/Instagram Devotional article of the week (tap to read full) Archive: past verses list (searchable) | Tap Share → pick app (WhatsApp, Instagram, etc.) Tap article → full screen read Scroll archive | GET /bible/today GET /devotion/articles | ← More Drawer ← Home verse card tap | Verse image is styled with org branding + verse text
📣 Announcements Screen | / announcements | Pinned and recent announcements | Pinned section: gold-border cards, pushpin icon Recent section: chronological list Urgency badge: 🟢 Normal ¦ 🟠 Important ¦ 🔴 Emergency Admin: + Create button (top right) | Tap card → full announcement Admin: create, pin/unpin, delete | GET /announcements | ← More Drawer ← Home banner tap | Expired announcements auto-hide
👨‍👩‍👧 Teams Screen | / teams | All teams in the organization | Team cards: team colour chip + name + leader photo + member count Tap to expand preview or navigate | Tap team card → Team Detail | GET /teams | ← More Drawer ← Members filter
👥 Team Detail Screen | / teams/:id | Members of one team | Team name header + leader info card (photo + name + contact) Member photo grid (3-column) Upcoming team events list | Tap member photo → Member Profile Tap event → Event Detail Tap leader phone → call | GET /teams/:id | ← Teams Screen
⚙️ Settings Screen | / settings | User profile and notification preferences | Profile section: avatar (tap to change) + name + phone (read-only) Notification toggles: Birthdays ¦ Events ¦ Prayer ¦ Announcements App Version label Logout button (bottom, red text) | Toggle notification categories on/off Tap Logout → confirm → clear tokens | GET /members/me PATCH /members/me/settings | ← More Drawer ← Home avatar tap

## 🔑 API Keys & Web Arch
🔑 API Keys, Credentials & Admin Website Architecture
All service credentials + full Next.js website structure + Google Sheet import guide (website-only feature)
🔑 SECTION A — API KEYS & ENVIRONMENT VARIABLES
Service | Environment Variables | Where to Get It | Used In | Required? | Free Tier? | Important Notes
Google Cloud (Sheets API) | GOOGLE_SERVICE_ACCOUNT_JSON (full JSON key file content) GOOGLE_SHEETS_SCOPE | console.cloud.google.com → IAM & Admin → Service Accounts → Create → Add Key → JSON | NestJS backend: read Google Sheet Next.js admin website: import feature | ✅ Yes | ✅ Free | Enable 'Google Sheets API' in the project. Share each Sheet with the service account email (found inside the JSON). Uses server-to-server auth — no user login popup needed.
Google Cloud (Drive API) | Same service account JSON | Same console project Enable 'Google Drive API' (separate toggle from Sheets) | NestJS: download member photos from Google Drive links in the sheet | ✅ Yes | ✅ Free | Google Forms uploads photos to Drive. Share the Drive folder with service account email OR make folder 'Anyone with link can view'.
Firebase (Cloud Messaging — Server) | FIREBASE_PROJECT_ID FIREBASE_CLIENT_EMAIL FIREBASE_PRIVATE_KEY (from Admin SDK service account) | console.firebase.google.com → Project Settings → Service Accounts → Generate new private key (JSON) | NestJS backend: send push notifications to all members | ✅ Yes | ✅ Free | Keep auth token only in .env, never commit. Add to .env and gitignore. Use ntfy HTTP API in NestJS (simple fetch/axios calls).
Firebase (Flutter App Config) | google-services.json → android/app/ GoogleService-Info.plist → ios/Runner/ | Firebase console → Project Settings → Your Apps → Add App → Download config file | Flutter app: receive push notifications FCM token registration | ✅ Yes | ✅ Free | Add Android app (bundle: com.yourorg.app) and iOS app separately. These files go into the Flutter project, not .env.
Plivo (free tier) / Termii (SMS OTP) | TWILIO_ACCOUNT_SID TWILIO_AUTH_TOKEN TWILIO_PHONE_NUMBER ── or ── Plivo_AUTH_KEY Plivo_SENDER_ID Plivo_TEMPLATE_ID | twilio.com/console ── or ── Plivo.com/dashboard | NestJS: send 6-digit OTP via SMS for member login | ✅ Yes | ⚠️ Paid (trials available) | Plivo recommended for India (cheaper, DLT registered). Plivo for international. DLT registration required in India for transactional SMS.
MinIO (Self-hosted) | MINIO_ENDPOINT=https://media.yourorg.com MINIO_ACCESS_KEY MINIO_SECRET_KEY MINIO_BUCKET=church-media | Set during MinIO Docker setup. Generate strong random keys: openssl rand -base64 32 | NestJS: store/serve all photos Admin website: photo uploads Flutter app: display photos via CDN URL | ✅ Yes | ✅ Free (self-hosted) | Expose MinIO behind Caddy with HTTPS. Use separate buckets: 'member-photos' and 'event-photos'. Enable public read on event-photos bucket.
JWT Secrets | JWT_SECRET JWT_REFRESH_SECRET JWT_EXPIRES_IN=15m JWT_REFRESH_EXPIRES_IN=7d | Generate locally: openssl rand -base64 64 (run twice for 2 different secrets) | NestJS: sign & verify all auth tokens | ✅ Yes | ✅ Free | Use different values for access vs refresh. Minimum 64 characters. Rotate every 90 days. Store ONLY in server .env — never in app code.
Cloudflare (CDN + DNS) | CLOUDFLARE_API_TOKEN CLOUDFLARE_ZONE_ID | dash.cloudflare.com → Profile → API Tokens → Create Token → Edit Zone DNS | CDN for photo delivery (MinIO → Cloudflare) DDOS protection | 🟡 Optional (strongly recommended) | ✅ Free plan | Point your domain NS to Cloudflare. Proxy MinIO subdomain through Cloudflare for fast photo loading across India.
GlitchTip (self-hosted) (Error Tracking) | GLITCHTIP_DSN_BACKEND GLITCHTIP_DSN_NEXTJS GLITCHTIP_DSN_FLUTTER | glitchtip.com → New Project → Choose platform → Copy DSN | NestJS crashes, Next.js errors, Flutter app crashes | 🟡 Recommended | ✅ Free (5k events/mo) | Create 3 separate GlitchTip (self-hosted) projects. Each gets its own DSN. Invaluable during early launch when bugs are common.
Apple Developer (iOS only) | Team ID, Bundle ID Distribution Certificate Provisioning Profile | developer.apple.com → Certificates, IDs & Profiles | Flutter iOS build + App Store / TestFlight | ✅ Yes for iOS | ❌ $99/year | Required ONLY to distribute on iPhone. Use TestFlight for beta testing members before public release.
Google Play (Android only) | Upload keystore file (JKS) KEYSTORE_PASSWORD KEY_ALIAS KEY_PASSWORD | Generate keystore: keytool -genkey -v -keystore upload-keystore.jks Play Console: play.google.com/console | Flutter Android build + Play Store | ✅ Yes for Android | ❌ $25 one-time | Keep the keystore file BACKED UP SAFELY — losing it means you cannot update the app. Store in password manager + encrypted backup.
🖥️ SECTION B — NEXT.JS ADMIN WEBSITE — PAGE ARCHITECTURE
Page Route | Page Name | Access Level | Key Components & Features | API Calls Made | Special Feature | Notes
/ | Login Page | Public | Org logo + name Phone number input (with +91 flag) Send OTP button 'Forgot access? Contact admin' link Footer: app version | POST /auth/send-otp POST /auth/verify-otp | Auto-redirect to /dashboard if session exists | OTP input shows as 6-box grid after phone submit
/dashboard | Dashboard Home | All Admins | Stats cards row: Total Members ¦ Events This Month ¦ Photos Uploaded ¦ Teams Birthday widget: this week's birthdays with photos Recent activity feed Quick actions: [Add Member] [Create Event] [Send Notification] [Import Members ←] | GET /analytics/summary GET /home/feed | Role-based card visibility (Analytics hidden from Media Admin) | Import Members quick action opens import wizard
/members | Members List | Super Admin Secretary | Searchable & sortable data table Columns: Photo ¦ Name ¦ Team ¦ Role ¦ DOB ¦ Status ¦ Actions Filter bar: team / alumni / active-inactive Bulk select → bulk delete / export Top right: [+ Add Member] [📥 Import from Google Sheet] | GET /members?sort=name&filter=... DELETE /members/:id | 📥 Import from Google Sheet button → opens import wizard page | Export to Excel button downloads current filtered list
/members/import | Import Members from Google Sheet | Super Admin Secretary | STEP 1 — Paste URL Large text input for Google Sheets URL [Validate & Preview] button Instructions panel (collapsible): how to share sheet, expected columns STEP 2 — Preview & Map Columns Table preview: first 5 rows of sheet data Column mapping dropdowns: match sheet column → member field Auto-detection highlights matched columns in green STEP 3 — Conflict Settings Radio: Skip duplicates ¦ Overwrite existing ¦ Ask per row Duplicate detection: by phone number STEP 4 — Import [Import X Members] confirm button Progress bar (animated) Live counter: Imported: 0 / Skipped: 0 / Errors: 0 STEP 5 — Results Summary card: ✅ 48 imported ¦ ⏭ 3 skipped ¦ ❌ 1 error Download Error Report (CSV) [View Members] button → /members | POST /members/import-sheet Body: { url, columnMap, conflictMode } Backend flow: 1. Extract Sheet ID from URL 2. Call Google Sheets API v4 3. Fetch photos via Drive API 4. Upload photos to MinIO 5. Save members to PostgreSQL 6. Return import summary | ⭐ CORE FEATURE Step-by-step wizard UI Auto column detection Live import progress Duplicate handling | Sheet must be shared with service account email. Photos are Google Drive links from Form file upload — fetched and stored in MinIO automatically.
/members/new | Add Member Manually | Super Admin Secretary | Form fields: Full Name, Phone, Email, DOB, Team (dropdown), Role (dropdown) Photo: drag-drop zone or file picker → preview + crop tool [Save] and [Save & Add Another] buttons | POST /members POST /media/upload (photo) | Photo crop tool (aspect ratio 1:1 enforced)
/members/[id] | Member Profile (Admin Edit View) | All Admins | All member fields displayed + inline edit form Team & role dropdowns Activity log: last login, events attended Delete / Archive buttons (with confirm dialog) Photo replace option | GET /members/:id PATCH /members/:id DELETE /members/:id | Unsaved changes warning on navigate away
/events | Events Manager | President Secretary Super Admin | Toggle: Calendar view ¦ List view Colour coded: 🔵 Church Event ¦ 🟡 Birthday ¦ 🔴 Feast Past / Upcoming tabs [+ Create Event] button | GET /events DELETE /events/:id | iCal export per event
/events/[id]/edit | Create / Edit Event | President Secretary Super Admin | Title, date/time pickers, location field Rich text description editor (Tiptap/Quill) Banner photo upload (no video) Team selector 'Send push notification on save' toggle | GET/PATCH /events/:id POST /notifications/send (if toggled) | Auto-notification on save | Banner must be photo — video not supported
/media | Photo Manager | Media Admin Super Admin | Album grid view Drag-drop multi-photo upload zone Tag photos to event dropdown Bulk delete Storage usage bar (MinIO quota) NOTE: Videos removed — photos only | GET /media/albums POST /media/upload DELETE /media/:id | Multi-file drag-drop Auto image compression (Sharp.js) before MinIO upload | PHOTOS ONLY — video upload removed from website too
/about/edit | Edit About Us Page | Super Admin | Rich text editor: org history, vision, mission Founder section: photo upload + bio text Executive Committee builder: — Add/remove committee members — Photo + name + designation per person — Drag to reorder Past Presidents timeline editor: add name + year range + photo Contact details + social media links editor [Publish Changes] button | GET /organization/about PATCH /organization/about POST /media/upload (committee photos) | Drag-to-reorder committee members Live preview panel (right side) | Changes reflect immediately in app's About Us screen
/notifications/send | Send Notification | President Super Admin | Compose: Title + Body (character count) Type selector: 🟢 Info ¦ 🟠 Important ¦ 🔴 Emergency Audience: All Members ¦ Team (dropdown) ¦ Individual (search) Schedule: Send Now ¦ Schedule for Later (datetime picker) Mobile preview mockup (right panel) | POST /notifications/send | Live mobile notification preview Scheduled sends via cron queue
/prayer | Prayer Schedule | Secretary Super Admin | Week grid: days × time slots Drag member name/photo into slot Colour per team Export schedule as PDF | GET /prayer/schedule PATCH /prayer/schedule | Drag-and-drop scheduling grid
/analytics | Analytics Dashboard | President Super Admin | Member growth line chart Attendance per event bar chart Team distribution pie chart Date range picker Export: PDF report ¦ Excel data | GET /analytics/* | Date range filtering Chart.js / Recharts
/settings | App Settings | Super Admin only | Org name + logo upload App theme colour Liturgical calendar config (feast days list) Admin account management (add/remove admins) API health checks panel Audit log viewer (who did what, when) | GET/PATCH /settings GET /audit-logs | API health check status indicators Audit log with filters
📋 SECTION C — HOW TO FETCH MEMBERS BY PASTING A GOOGLE SHEET URL (Website-only feature)
Step | Layer | What Happens | Code / Implementation | Key Detail | Common Error | Fix
STEP 1 📋 Prepare the Sheet | Google Workspace (One-time setup) | Create a Google Form for student registration with these fields: ① Full Name (Short answer) ② Date of Birth (Date) ③ Phone Number (Short answer) ④ Email (Short answer) ⑤ Team / Group (Dropdown) ⑥ Profile Photo (File upload) Responses auto-save to a linked Google Sheet. | In Google Form: Settings → Responses → Link to Sheets In the linked Sheet: Share → Change → Anyone with link → Viewer Also share with service account email: your-sa@project.iam.gserviceaccount.com | The service account email is inside the JSON key file you download from Google Cloud Console. | 403 Forbidden when fetching | Sheet not shared with service account email. Share it manually each time you have a new batch.
STEP 2 🔗 Admin Pastes URL (Website) | Next.js Frontend (/members/import) | Admin opens /members/import in the website. Pastes the Google Sheet URL into the input box. Clicks 'Validate & Preview'. Frontend extracts the Sheet ID from the URL using regex. | // Extract Sheet ID from any Google Sheets URL const extractSheetId = (url) => { const match = url.match( /\/spreadsheets\/d\/([a-zA-Z0-9-_]+)/ ); return match ? match[1] : null; }; // Then POST to backend: await fetch('/api/members/preview-sheet', { method: 'POST', body: JSON.stringify({ sheetId }) }); | Works with all Google Sheets URL formats: • /edit#gid=0 • /edit?usp=sharing • /pub?output=csv (all contain the same Sheet ID pattern) | Sheet ID not extracted | URL must contain /spreadsheets/d/. If user pastes a csv export URL, the regex still works.
STEP 3 📊 Backend Reads Sheet | NestJS Backend (Google Sheets API v4) | NestJS receives the Sheet ID. Authenticates with Google using the Service Account JSON (stored in .env). Fetches all rows from Sheet1 columns A–Z. Returns the raw 2D array to the frontend for preview. | import { google } from 'googleapis'; async previewSheet(sheetId: string) { const auth = new google.auth.GoogleAuth({ credentials: JSON.parse( process.env.GOOGLE_SERVICE_ACCOUNT_JSON ), scopes: [ 'https://spreadsheets.google.com/feeds', 'https://www.googleapis.com/auth/drive.readonly' ], }); const sheets = google.sheets({ version: 'v4', auth }); const res = await sheets.spreadsheets.values.get({ spreadsheetId: sheetId, range: 'Sheet1!A1:Z500', }); return res.data.values; // 2D array, row 0 = headers } | Row 0 is the header row (column names from the Form). Rows 1+ are member data. Empty cells return as undefined — handle with ?? '' | Error: The caller does not have permission | Sheet is not shared with the service account email. The SA email looks like: name@project-id.iam.gserviceaccount.com
STEP 4 🗂️ Auto-Map Columns (Website preview) | Next.js Frontend + NestJS | Frontend receives the 2D array. Displays first 5 rows as a preview table. Attempts to auto-detect column mapping by comparing header names to known aliases. Shows mapping dropdowns — green for matched, yellow for unmatched. Admin confirms or adjusts mapping. | const ALIASES = { full_name: ['name','full name','student name','your name'], dob: ['date of birth','dob','birthday','birth date'], phone: ['phone','mobile','contact number','phone number'], email: ['email','email address','e-mail'], team: ['team','group','unit','wing'], photo_url: ['photo','image','profile photo','file upload'] }; function autoDetect(headers) { return headers.map(h => { const lower = h.toLowerCase().trim(); for (const [field, aliases] of Object.entries(ALIASES)) { if (aliases.some(a => lower.includes(a))) return field; } return 'ignore'; }); } | Google Forms uses the question text as the column header. Name your form questions clearly (e.g. 'Full Name' not 'Q1') for best auto-detection. | All columns map to 'ignore' | Form question names don't match any aliases. Fix: rename form questions to standard names, or manually use the mapping dropdowns.
STEP 5 🖼️ Fetch Member Photos (Google Drive) | NestJS Backend (Drive API) | Google Forms saves uploaded photos to a Drive folder. The sheet contains a Drive URL per member. Backend downloads each photo using Drive API and re-uploads to MinIO. The MinIO URL is stored in the member record. | // Extract Drive file ID from any Drive URL function getDriveId(url: string) { const patterns = [ /\/file\/d\/([\w-]+)/, /id=([\w-]+)/, /\/open\?id=([\w-]+)/ ]; for (const p of patterns) { const m = url?.match(p); if (m) return m[1]; } return null; } // Download from Drive, upload to MinIO async migratePhoto(driveId, auth, memberId) { const drive = google.drive({ version: 'v3', auth }); const stream = await drive.files.get( { fileId: driveId, alt: 'media' }, { responseType: 'stream' } ); return await this.minioService.upload( stream.data, `members/${memberId}.jpg` ); } | Photos in Drive are private by default. EITHER: Share the Form's response folder with the service account email. OR: In Google Form settings → Response storage → set folder to 'Anyone with link'. | 403 when downloading photo | Drive photo folder not shared with service account. Go to Drive → find the Form responses folder → Share with SA email.
STEP 6 💾 Save to Database | NestJS Backend (PostgreSQL via Prisma) | Each mapped row becomes a Member record. Duplicate detection by phone number. Conflict mode chosen by admin (skip / overwrite / merge). Sorted alphabetically after bulk insert. Import summary returned: imported count, skipped, errors. | async importMembers(rows, map, mode) { const results = { imported:0, skipped:0, errors:[] }; for (const row of rows) { try { const data = this.mapRow(row, map); if (!data.phone) { results.errors.push(row); continue; } const exists = await this.prisma.member .findUnique({ where: { phone: data.phone } }); if (exists) { if (mode === 'skip') { results.skipped++; continue; } if (mode === 'overwrite') await this.prisma.member.update( { where: { id: exists.id }, data }); } else { await this.prisma.member.create({ data }); results.imported++; } } catch(e) { results.errors.push({ row, error: e.message }); } } return results; } | Phone number is the unique key for duplicate detection (not email) since all members have a phone number from OTP login. | Prisma unique constraint error | Two rows have the same phone number. The conflict mode handles this — set to 'skip' for safe first import.
STEP 7 ✅ Result & App Sync | Website + Flutter App | Website shows success summary: ✅ 48 members imported ⏭️ 3 skipped (duplicates) ❌ 1 error (missing phone) [Download Error Report CSV] button [View All Members] button Flutter app: next time any member opens the Members screen, it fetches the updated list from the API and displays all newly imported members sorted A–Z. | // Website (Next.js) if (result.success) { toast.success( `${result.imported} members imported!` ); router.push('/members'); } // App auto-refreshes on screen focus: // Flutter uses ref.invalidate(membersProvider) // or pull-to-refresh on Members screen. // No manual sync needed in app. | The app does NOT have the import feature. It only displays the results. All importing happens exclusively on the admin website. | Members not showing in app after import | App is using cached data. Pull down to refresh on Members screen. Cache TTL is 5 minutes.